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Budget Reallocation Limits
Focus of this document is the approval mechanism during Contract Award, Contract Amendment and Budget reallocation during a project life cycle. Major assumptions are as below:
· Architecture Lead is responsible for budget up to DD
· PD is responsible for the budget post DD handover
· The CRN system will be simplified to reduce day-to-day amendment approvals.

1. Contract Award Approval Matrix

	Variation of Likely Award Amount from Contract Value
	Approval Authority
(in addition to Procurement DOA as per Financial Authority  Delegation (FAD) Policy)

	Rs 10,000 or 0.25% of Budgeted value
	Package Head (with prior information to PD/PMH (before issuance of LOI/WO))

	1% of Budgeted Value
	HOD-Procurement (with prior information to PD/PMH (before issuance of LOI/WO))


The Variation amount to be utilised from execution contingency
2. Amendment approval matrix

A. Limits for amendment approval for services by Commercial Manager:
	Original Contract Value (as awarded)
	Max. cumulative Increase on account of amendment from original contract value (Due to additional scope or rate variations)

	10 L
	25% of original contract value

	10.01 – 25 L
	15% of original contract value or Rs. 2.5 L, whichever is higher

	25 L – 50 L
	10% of original contract value or Rs. 3.275 L, whichever is higher

	> 50 L
	5 Lacs


· Where only quantity variation occurs, variation at any value can be approved by commercial manager (Subject to budget reallocation process)
· All amendments above these limits shall require PD/COO* approval


B. Limits for amendment approval for Lodha Supply Materials by Commercial Manager 
	Material Type
	Category Characteristics
	Amendment limit by Commercial Manager (% of original quantity)

	Category A
(Steel, concrete, CP/Sanitary fitting)
	High cost
	0%

	Category B
(Doors, Electrical, HVAC, Kitchens, plumbing fixtures etc as defined in Annexure 1)
	Medium cost or medium estimation variability
	10%

	Category C
(Tiles, Blocks, CP Accessories etc as defined in Annexure 1)
	Low cost or high estimation variability
	25%


· All amendments above these limits shall require PD/COO* approval.
3. Budget Reallocation Process
The value and type of allocation for the various contingencies (beyond the basic construction cost for each plant) are:
· DD Contingency – 6%, allotted at L1 level
· Execution Contingency – 6%, allotted at L1 level
· Construction Discretionary Budget- Allotted at plant level – Usage norms as defined currently
· Design Discretionary Budget- Allotted for select packages – Usage norms as defined currently
· HFM Discretionary Budget - Allotted at Project level as part of Infra Plant for that project. Approvals to be handled as per norms defined in FAD policy.
Note: Inflation upto expected point of award is already taken into account in the individual L3 package budgets.
DD Contingency:
DD Contingency is primarily to be used between the period of Concept Budget finalization and (95%) completion of DD for that package. Once DD for a L1 package is completed, any surplus amount of DD contingency shall be moved to Execution contingency budget.  
	Change
	Approval by
	Key questions by approver

	Use of DD contingency within a L1 package
	1. Design cell package Lead + DCO package Lead + Architecture cell project Lead through DCO project Lead

All leads to be level 2 or higher
	1. Has complete value engineering been done and no further reduction in budget feasible

	Allocation of DD contingency of one package to another

	Level 1 of Architecture incharge of the project, through DCO Project Lead.
	· Is contingency within L1 package not sufficient
· Is contingency remaining, sufficient for the package from which budget being moved

	Plant budget increase due to DD contingency being exceeded
	RCEO as per ‘Budget modification – steps to be followed’ policy
	· Entire budget reviewed for VE options & reallocation within plant budget



Design Discretionary Budget: 
DesignDiscretionary Budget can be used anytime post Concept Budget – it applies only to KCA finishing within the building line and Landscape & KCA finishing in the Infra plant. 
	Change
	Approval by

	Allocation/use of Design Discretionary Budget
	Level 1 of Architecture incharge of the project, through DCO Finishing Package Lead / Landscape package Lead


Construction Discretionary Budget
ConstructionDiscretionary Budget can be used anytime post Concept Budget
	Change
	Approval by

	Allocation/use of Construction Discretionary Budget
	PD / CH / DCH (highest level CM associate working full time on the project); PMH can formulate rules for his projects wrt usage and reporting of this budget



Budget change for any L3 tender group on account of Contract Award or Amendment
	Change
	Initiator
	Approver

	Reallocation to different contracts within L3 tender group 
	DCO project Lead for the package (prior to award of all the contracts in a L3 tender group) OR Commercial Manager (anytime)
	Approval not needed

	Allocation of Execution contingency to L3 tender group 
	Commercial Manager
	PD/COO*

	Plant Budget Increase (if project contingency available for a given tender is exhausted)
	Commercial Manager
	RCEO (adjustment in SAP done by DCO)



* For projects which do not have a PD.








Annexure 1: 
Material group as per Old Material Master Grouping (Table 1) and the New Material Master Grouping (Table 2)
Table 1: Old Material Master Grouping
	Material Group
	Material Group Description
	Description 2 for the material group
	Threshold (%)

	Category A

	113
	Civil Works
	Precast RCC
	0%

	310
	Concrete
	Concrete
	0%

	320
	Reinforcements
	Reinforcements
	0%

	340
	Precast Concrete
	Precast Concrete
	0%

	510
	Struc. Metal Framing
	Structural Metal Framing
	0%

	2230
	Plumbing Equipments
	Plumbing Equipments
	0%

	2240
	Plumbing Fixtures
	Plumbing Fixtures
	0%

	R0321
	Reinforcements-TOR
	Reinforcements-TOR
	0%

	Category B

	202
	Finishing Work
	Wooden Sections
	10%

	206
	Finishing Work
	Ready Made Doors
	10%

	230
	Finishing Work
	Carpets
	10%

	390
	Shuttering Materials
	Shuttering Materials
	10%

	501
	Electrical
	Substation
	10%

	550
	Metal Fabrications
	Metal Fabrications
	10%

	590
	Roofing
	Roofing
	10%

	620
	Finish Carpentry
	Finish Carpentry
	10%

	640
	Arch. Woodwork
	Architectural Woodwork
	10%

	680
	Composite Fabricns.
	Composite Fabrications
	10%

	690
	Wood and Timber
	Wood and Timber
	10%

	701
	Fire Fighting
	Fire Extinguisher
	10%

	820
	Doors
	Doors
	10%

	840
	Curt. Walls &Entrnc
	Curtain Walls and Entrances
	10%

	850
	Windows
	Windows
	10%

	870
	Hardware
	Hardware
	10%

	880
	Glazing
	Glazing
	10%

	930
	Tiling and Flooring
	Tiling and Flooring
	10%

	1120
	Commercial Equipment
	Commercial Equipment
	10%

	1130
	Residential Equip.
	Residential Equipment
	10%

	1140
	Food Service Equip.
	Food Service Equipment
	10%

	1150
	Edu. & Sci. Equip.
	Educational and Scientific Equipment
	10%

	1160
	Entertainment Equip.
	Entertainment Equipment
	10%

	1404
	Quality Equip & Acc
	Guages& Meters
	10%

	2120
	Fire Ext. Sys.
	Fire Extinguishing Systems
	10%

	2130
	Fire Pumps
	Fire Pumps
	10%

	2210
	Piping and Pumps
	Piping and Pumps
	10%

	2305
	HVAC Works
	HVAC Works
	10%

	2550
	Intg Auto. Fac.Cont.
	Integrated Automation Facility Controls
	10%

	2605
	Electrical Work
	Electrical Work
	10%

	2610
	MV Elect. Distn.
	Med. Voltage Electrical Distribution
	10%

	2620
	LV Elect. Distn.
	Low Voltage Electrical Distribution
	10%

	2720
	Data Communications
	Data Communications
	10%

	2730
	Voice Communications
	Voice Communications
	10%

	Category C

	112
	Civil Works
	Masonry
	25%

	228
	Finishing Work
	Partitions
	25%

	405
	Masonry
	Masonry
	25%

	920
	Plastering & Gypsum
	Plastering and Gypsum Boards
	25%

	970
	Wall Finishes
	Wall Finishes
	25%

	1420
	Elevators
	Elevators
	25%

	1430
	Escalators
	Escalators and Travalators
	25%

	1440
	Lifts
	Lifts
	25%

	1490
	Other Convey. Equip.
	Other Conveying Equipments
	25%

	1701
	Infra Str Facilities
	Gym Equipment
	25%

	2650
	Lighting
	Lighting
	25%



Table 2: New Material Master Grouping
	Material Group
	Material Group Description
	Threshold (%)

	Category A

	7009
	Concrete
	0%

	7016
	CP Fitting
	0%

	7059
	Sanitary ware
	0%

	7064
	Steel
	0%

	Category B

	7003
	Brown Goods (Small Appliances)
	10%

	7004
	Carpentry
	10%

	7012
	Construction Plant and Machinery
	10%

	7019
	Door / Window Hardware
	10%

	7020
	Door Frame
	10%

	7021
	Door Shutter
	10%

	7023
	Electrical
	10%

	7024
	Electrical Panels
	10%

	7033
	HVAC
	10%

	7035
	Interior Furnishing & Accessories
	10%

	7045
	Modular Kitchen
	10%

	7051
	Piping and Fixtures
	10%

	7052
	Plumbing
	10%

	7053
	Power Backup Systems
	10%

	7054
	Prefabricated
	10%

	7055
	Pump
	10%

	7063
	Specialist Formwork
	10%

	7065
	Stone
	10%

	Category C

	7001
	Architrave
	25%

	7002
	Broken Tiles
	25%

	7005
	Cement
	25%

	7006
	Cement Additives
	25%

	7007
	Children's Play Equipment
	25%

	7008
	Commercial Appliances
	25%

	7013
	Consumer Electronics
	25%

	7014
	CP Accessories
	25%

	7015
	CP Extensions
	25%

	7017
	Curb stone
	25%

	7022
	Earthing
	25%

	7025
	Electrical Tools
	25%

	7026
	Flooring
	25%

	7028
	Furniture
	25%

	7029
	Galvanised Iron
	25%

	7031
	Gym Equipment
	25%

	7040
	Lighting
	25%

	7041
	Lightning Protection
	25%

	7042
	Lipping Patti
	25%

	7043
	Masonry
	25%

	7044
	Mild Steel
	25%

	7048
	Outdoor Accessories
	25%

	7050
	Paver blocks
	25%

	7057
	Ready Mix Plaster
	25%

	7061
	Security Equipment
	25%

	7062
	Spa Equipment
	25%

	7066
	Storm Drainage
	25%

	7069
	Tiles
	25%

	7070
	Upholstery
	25%

	7072
	Vertical Transport
	25%

	7073
	Wall Paper
	25%

	7074
	Water Filtration
	25%

	7075
	White Goods (Major Appliances)
	25%
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