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Lodha Crown-Aspiration
	Particulars
	Discussion
	Remarks

	Presentation by KAPL
	The overall facade was presented by KAPL for Lodha Crown.
	

	Typical Lobby
	1. The fins in the typical lobby to be replaced with planters.
2. The railing on the typical lobby parapet to be avoided & parapet wall height to be increased. 
	KAPL to modify the parapet wall section of the typical corridor.

	Unit Plan
	The window sizes to be retained & not to be reduced further.
	

	Apartment Windows 
	1. The window screen (lower portion) to be retained with sliding window.
2. The sliding windows will be in upper as well as lower part but with N-1 as per policy. 
3. The option of fixed fritted glass (in champagne gold) in the lower portion of the window also to be checked.
	

	Internal Facade 
	The internal facade to be optimized in terms of cost by the use of precast fins for the toilet shafts & no screen for any windows on that facade.

	




	Mock Up
	A mock up of a complete window section along with the curved RCC corner of the bldg to be done & checked at site for finish & execution feasibility.
  
	





	 
	 
	 
	 

	
	PALAVA CROWN- VE OPTIONS  DISCUSSED
	
	

	S.NO.
	DETAIL
	RATE @ RS/SQ.FT.
	REMARKS

	A
	Overall cost as per norms including infra
	5250
	 

	B
	current cost including infra
	5665
	increase of 470 Rs/ sq.ft.

	 
	 
	 
	 

	C
	Major contribution to increased costs is façade 
	342
	cost norm of 315 vs. current design cost @ 657 Rs/sq.ft.

	D
	Façade elements which are major contributors
	 
	 

	1
	Fins in entrance lobby
	91
	 

	2
	Fins of toilet shaft on the core side
	80
	due to unit design having more exposed surface

	3
	Screen infront of lower window portion
	60
	 

	4
	increase of texture paint areas
	30
	due to unit design having more exposed surface

	5
	Sliding window in the lower portion behind the screen
	10
	 

	6
	increased window to carpet area ratio
	45
	This is due to increased ratio from  general 15 % to 20 % ( in splendora & Luxuria  it is 15%  belmondow T 12- 24%) in crown it is 38%

	 
	Sub total
	316
	Approx 316 rs/sq.ft. post policy impact removal

	 
	 
	 
	 

	E 
	Suggested VE options
	 
	 

	1
	lower part of the window to have fixed glass + frit pattern & no screen
	55
	This some saving will be achieved if the fritted glass option is finalized.

	2
	Removal lobby fins and provide planters
	75
	Accepted by all stakeholders.

	3
	reduce window areas by 10%
	45
	Window size remains unchanged, hence no saving.

	4
	Replacing toilet shaft fins with precast screens. (Internal facade.)
	35
	Accepted by all stakeholders.

	 
	Sub total of saving possible
	210
	 

	
	
	
	



