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The Following Points were discussed to way forward
	Particulars
	Discussion
	Action By
	Date
	Remarks

	Structural
	Balcony line needs to be finalized for structural co-ordination in unit plans.
	Lodha Laision
	07-12-2013
	Current column locations are fine. Balcony lines will be adjusted accordingly.

	Structural
	Lift blocks for A typology buildings to have structural wall separating the 2 lifts.
	SJCSE/ Struct.Bom
	
	Closed

	Structural
	All the apartment terrace beams to be 200/150mm wide
	SJCSE/ Struct.Bom
	
	Closed

	Structural/ MEP/Architectural
	To eliminate the sunk strip, need to look out for the drain pipe option as discussed & that can be adopted in the conventional system. But currently we shall proceed with the sunk strip in Mivan system. The sunk strip to be relocated as discussed.
	WSP/Lodha MEP/KAPL
	
	Sunk strip eliminated as per dwg received on 13-12-13. But the drain cut out location to be mentioned by KAPL.

	Structural
	All the lintel heights to be at 2250m.(as per revised policy) 
	SJCSE/ Struct.Bom
	
	Conveyed to all & noted.

	Structural
	Apartment terrace for the A & B typology to have a non structural notch at the end of the beam in order to maintain the carpet areas.
	SJCSE/ Struct.Bom
	
	Consultants to revert.

	Structural
	The terrace beam depth below the sunken part to match with the soffit of the other beams.
	SJCSE/ Struct.Bom
	
	Closed

	MEP
	Geysers currently shown above the wash basins have to be relocated in the bath/shower areas.
	WSP
	
	Closed for A. For Typology B dwgs still awaited.

	MEP
	The floor trap of the bath area to be on the shower head side. Provide separate floor trap for W.C also.
	WSP
	
	Closed with comments-Correct legend for FD  in A typology.

	MEP
	For the exhaust fans in the toilet In line option to be considered, for the situation where the w.c, wash basin & bath are physically separate  in line and have a window opening  only at one end or where there is no ventilation to the toilet areas.
	WSP
	
	Closed for A typology. Awaiting B typology dwgs.

	MEP
	A latest co-ordinated MEP layout of both typologies typical floor to be provided.
	WSP
	
	Dwgs incorporating comments as discussed on 13-12-13 to be submitted.


	MEP
	Service slabs of the buildings can have the ODU’s stacked above each other wherever the bedroom window is at a higher level.
	WSP
	
	Comments- A2 typology ODU 1 & 10 to be stacked above each other in front of the toilets by increasing the service slab width. Similarly for B typology.  

	MEP
	The machine room less lift section to be provided. Also indicate the opening for access/ventilation.
	WSP
	
	Dwg awaited.

	Architectural/MEP
	Toilet window height has increased by 100mm due to increase in lintel height as per policy. Please refer the sketch attached. It should be a louvered window with no openable shutter due to cost parameters. WSP to confirm the opening size w.r.t. the passage of ODU through it& service access.
	KAPL, WSP
	
	WSP/KAPL to confirm.

	Architectural
	Kitchen dimension of 7’6” to be revised to 7’9” in B type.
	KAPL
	
	Closed

	MEP
	IDU to be centered with the walls. Typology A2 Living room IDU to be shifted on the shorter side of the wall with pelmet. For the Study the IDU to be shifted over the bed.
	WSP
	
	Revised dwgs to be submitted.

	MEP
	For A typology only the master bedroom to have split air conditioner. The other rooms will only have a sleeve provision. 
	
	
	To be noted.

	MEP
	Ledge wall below wash basin to be deleted where ever the structure beam/column is not there.
	KAPL/SJCSE/ Struct.Bom
	
	

	MEP
	Meter room Section required through cut out for the riser. Aslo cut out dimension in the electrical shaft is required.
	WSP
	16-12-13
	Dwg required by EOD

	MEP
	Walls of electrical & FF shafts for Mivan to be in block work & sleeve dimensions & locations to be given.
	WSP/KAPL
	
	

	Architectural
	Ground floor Staircase door to open outside in the lobby.
	KAPL
	
	

	Architectural/MEP
	FF Door size-900 x 1400mm
Electrical door – 900 x 2100mm
Meter room door- 1200 x 2250mm.
The lintel height will be 2250mm.
Please note that there will be a 1 foot high brick work for the duct doors for fall protection.
	WSP/KAPL
	
	Widths confirmed but the heights to be finalized during finishing. 


			
