Palava 2 - Sector 3, Buildings
MOM-24  on 13-01-15
Attendees:
	LODHA
	KAPL
	
	

	Ajay Gandhewar
	Ebrahim
	
	

	Supriya Ambavane
	Digisha
	
	

	Mayuresh Kelvalkar
	Supriya
	
	

	Gauri Kulkarni
	Riyaz
	
	

	Srinivas Hoizal
	
	
	

	Rajeev Balasubramanian 
	
	
	

	Veera Banothu 
	
	
	

	
	
	
	

	S.no.
	Discussion
	Action By
	Date
	Remarks

	1.
	
Design Control Unit
a) KAPL finalized toilet options for both A & B typology.
b) B typology first cut finishing drgs. for review – 16-01-14
c) Toilet tile drop to be towards inside of door shutter.
d) Door with combined knob handle & lock centre to be at 950mm from flr. lvl.

	KAPL

	
	Attached list of tiles finalized for DCU.

	2.
	

a. CM team proposed to have marble sill at bottom for conventional buildings.
b. CM team to further discuss the same with Lodha facade team & Aluminium window vendor.
c. KAPL confirmed for conventional building window template sizes will be after plastering. Ex: if masonry opening is 1350mm wide aluminium window size will be 1325mm wide considering 1 coat of 12.5mm thk.  Plastering on either side.
d.  KAPL to give details of interface of external & internal finishes with aluminium frames. 








	Lodha Facade/
KAPL
	
	Lodha Design to share aluminium window shop  drgs. with KAPL

	3.
	
Design Deliverables

a. NC  option for Reckli – 07-01-15
b. C Bdlg. elevation grooves – 09-01-15 / 14-01-15
c. VFC Finishing drgs. B typology (wastage to be within 5%) -27-01-15 – KAPL to expedite
d. Building connection – KAPL to review & revert.
e. NC B type electrical drgs. with updated Drg. nos. – 07-01-15
f. NC B type refuge floor VFC – 09-01-15 / 13-01-15
g. NC B type electrical layouts – 16-01-15
h. C  A & B type refuge floor & electrical layouts – 23-01-15
i. Casa Viento centreline VFC – 09-01-15 / 15-01-15
j. Al. Window interface with external & internal finishes detail – 23-01-15

	KAPL
	
	Reckli 1/05 finalized  received & meeting with Reckli team next week.

	4.
	
R.C.C. screen

Lodha facade to review costing & revert


	Lodha Facade
	
	

	5.
	
Stone cladding at Building Entrance

Lodha to inform KAPL budgetary cost for stone.(sent on 07-01-14)
KAPL to propose stone cladding


	KAPL
	TBC
	

	6. 
	
Wardrobe & Chajja connection in conventional
[image: ]

Provide R.C.C pardi connection between wardrobe & Chajja
	SJSCE
	16-01-15
	

	
	
	
	
	

	7.
	A1- 8th floor refuge separate flat to have the exhaust fan within the ventilator. It would require size of the opening to be 250 x 250mm
	KAPL
	To be noted 
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