Palava 2 - Sector 3, Buildings
MOM-14  on 05-08-14 
Attendees:
	LODHA
	KAPL
	SJCSE/Struc Bom
	WSP

	Supriya Ambavane
	Ebrahim 
	Musthafa Shaju
	

	Mayuresh Kelvalkar
	Karim
	Mayur Kapadia
	

	Gauri Kulkarni
	Digisha
	
	

	Veera Banothu
	Karishma
	
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	



	S.no.
	Discussion
	Action By
	Date
	Remarks

	1.
	Casa Viento- Building setting out plan. 
a) KAPL to present facade strategy.
b) PBB to propose a layout showing drop off points for wings C & D
c) Lodha to review & revert.
d) WSP to review services routing & revert.
	Lodha Design/PBB/KAPL/WSP
	08-08-2014
	

	2.
	GRC- Final design pattern to be issued.
	KAPL
	14-08-2014
	

	3.
	Railing Design: Terrace & Utility final design pattern to be issued.
	KAPL
	14-08-2014
	

	4.
	Door window schedule – Ground floor (all typologies convention & non conventional bldgs)Priority clusters Uno & Elite
	KAPL
	08-08-2014
	

	5.
	VFC Ground floor plans-Conventional bldgs
	KAPL
	11-08-2014
	B3 & A2 first cut VFC to be recvd on Wednesday i.e 06-08-2014

	6.
	VFC First floor plans-Conventional bldgs
	KAPL
	14-08-2014
	

	7.
	First floor framing plans-Non Convention

A1: VFC  to be issued on 11-08-2014
A2: VFC  to be issued on 11-08-2014
B1: VFC  to be issued on 11-08-2014
B2: VFC  to be issued on 08-08-2014
B3 :VFC  to be issued on 06-08-2014




	SBC
	AS PER DATES MENTIONED
	

	
	
	SJCSE
	
	

	8.
	First floor framing plans- Convention

A1: VFC  to be issued on 11-08-2014
A2: VFC  to be issued on 11-08-2014


B1: Incorporate comments & send for approval by 06-08-2014
B2: Send first cut framing plans for comments by 06-08-2014
B3 : Send first cut framing plans for comments by 06-08-2014




	SBC
	AS PER DATES MENTIONED
	

	
	
	SJCSE
	
	

	9.
	Revised Plinth Beams for Conventional B2
	SJCSE
	06-08-2014
	

	10.
	Revised Footing for B type
	SJCSE
	06-08-2014
	

	11.
	Staircase Structural dwg
	SJCSE
	13-08-2014
	

	12.
	VFC First floor Architectural plans- Convention

	KAPL
	14-08-2014
	First cut VFC to be recvd on Monday i.e 11-08-2014

	13.
	VFC  Typical floor framing plans- Non-Convention.

	SBC/SJCSE
	12-08-2014
	Soft Copies for review  on 06-08-2014




