Dear All,

Please find attached the details for all 10 sets of Aluminium Formwork being used in Phase 1 (CBG)

Current Status:
1. 4 Sets (vendor MIVAN) will get free from CBG by Sep’13 –post that redesigning for Palava 2 buildings will take ~3 months
1. 3 Sets (vendor MIVAN) will get free from CBG by Jan 14 (add another ~3 months for redesign)
1. 1 Sets (Vendor MIVAN) will get free from CBG by Jan 14 (add another ~3 months for redesign)
1. 2 Sets (Vendor Maini) will get free from CBG in Aug 13 and Nov 13 – redesigning for Palava 2 building may be an issue with these sets 

Shared this with Shaishav and following can be considered as way forward for Palava 2 design:

1. First six buildings to be done using conventional system (as 6 sets of MIVAN will be available from CBG only by Jan 14)
1. Subsequent six buildings to be done using MIVAN system

Please let me know if any more detail required on this.

Mohit

